# Project Management Documents

Amaranth v2 — WBS, timeline, risks, resources and change log

2026-10-19

# Document control

| Field | Value |
| --- | --- |
| Title | Project Management Documents |
| Document ID | AMR-DOC-12 |
| Version | 1.0 |
| Date | 2026-10-19 |
| Author | Amaranth development team [TO CONFIRM: names] |
| Status | Final draft for defense |
| Sources | git history (183 commits, 82 merged branches), docs/v2/PLAN.md, docs/v2/PLAN-PHASE2.md, docs/v2/PROGRESS.md |

# Contents

- Approach

- Work breakdown structure (WBS)

- Timeline

- Milestones

- Risk register

- Cost and resources

- Change log

- Lessons learned

# 1. Approach

Incremental delivery, one feature per branch: each feature branch starts from develop, passes the gates (npm run check, and npm run db:test for database work), is merged with a merge commit into develop, and is recorded in docs/v2/PROGRESS.md. Plans were approved before large changes (docs/v2/PLAN.md, PLAN-PHASE2.md). Releases go to main through a pull request.

# 2. Work breakdown structure (WBS)

| WBS | Work package | Branches (examples) | Status |
| --- | --- | --- | --- |
| 1 | Project setup | docs/phase2-plan, feature/tooling-design-system | Done |
| 2 | Database | feature/db-v2-schema, feature/salingkusog-db, feature/statistics | Done |
| 2.1 | Newsroom schema, RLS, workflow | feature/db-v2-schema | Done |
| 2.2 | Salingkusog schema and views | feature/salingkusog-db | Done |
| 2.3 | Statistics schema | feature/statistics | Done |
| 3 | Authentication and access | feature/auth-staff, feature/publish-permissions, feature/salingkusog-team-access | Done |
| 4 | Public site | feature/public-shell-home, feature/section-pages, feature/article-page, feature/search-archives, feature/submissions-contact, feature/nav-more-menu, feature/section-* (12) | Done |
| 5 | Newsroom (CMS) | feature/cms-shell-dashboard, feature/cms-article-editor, feature/cms-editorial-workflow, feature/cms-media-library, feature/cms-people-board, feature/cms-site-settings | Done |
| 6 | Salingkusog module | feature/salingkusog-* (13), feature/sports-landing, feature/sk-* (5), feature/countdown-* | Done |
| 6.1 | Setup, import, scorekeeper | feature/salingkusog-cms-setup, feature/salingkusog-scorekeeper | Done |
| 6.2 | Public hub | feature/salingkusog-medal-tally, -schedule, -winners, -factions, -sports-bracket, -match-recap, -venues | Done |
| 6.3 | Automation | feature/sk-auto-brackets, feature/sk-contests, feature/sk-official-tally, feature/sk-points-race-ranges | Done |
| 7 | Branding | feature/brand-* (6) | Done |
| 8 | SEO, performance | feature/seo-sharing, feature/perf-pass, perf/edge-cache-images | Done |
| 9 | Security | fix/security-hardening, feature/turnstile-captcha | Done |
| 10 | Quality and polish | feature/v2-polish, fix/* | Done |
| 11 | Documentation | docs/*, this package | In progress |
| 12 | Acceptance and release | PR #6 develop → main (merged); manual tests MT-01 – MT-20 | Release done; manual tests [TO CONFIRM] |

# 3. Timeline

| Period | Work | Evidence |
| --- | --- | --- |
| 2025-09-23 – 2025-10-12 | v1 partial front end (16 commits) | git history |
| 2026-04-12 – 2026-04-13 | Interim admin and article pages (6 commits) | feature/admin, feature/article-card, feature/article-details-page |
| 2026-10-17 | v2 Phase 1: plan, database, tooling, public site, newsroom, SEO, performance (54 commits) | docs/v2/PROGRESS.md |
| 2026-10-18 | Phase 2: Salingkusog A1–A13, section layouts B1–B12, statistics, Brand 2026, edge cache (81 commits) | docs/v2/PROGRESS.md |
| 2026-10-19 | Publishing permissions, security, Turnstile, auto brackets, contests, official tally (25 commits so far) | docs/v2/PROGRESS.md |
| 2026-10-26 – 2026-10-30 | Salingkusog 2026 (from the live edition record) | sk_editions |
| [TO CONFIRM] | Defense presentation | — |

PM-1 — v2 timeline. Future dates are placeholders.

Note: the dense v2 dates reflect the commit history. Planning, design (Figma) and review time before and between commits are not visible in git [TO CONFIRM actual effort].

# 4. Milestones

| ID | Milestone | Date | Status |
| --- | --- | --- | --- |
| M1 | v2 plan approved | 2026-10-17 | Done |
| M2 | Newsroom and public site complete (Phase 1) | 2026-10-17 | Done |
| M3 | Salingkusog module and section layouts (Phase 2) | 2026-10-18 | Done |
| M4 | Brand 2026 approved by the Executive Editor and applied | 2026-10-18 | Done |
| M5 | Security hardening and CAPTCHA | 2026-10-19 | Done |
| M6 | Automatic brackets, round robins and contests | 2026-10-19 | Done |
| M7 | Release to main (pull request #6) | 2026-10-19 | Done |
| M8 | Salingkusog 2026 run on the system | 2026-10-26 – 30 | Upcoming |
| M9 | Defense | [TO CONFIRM] | Upcoming |

# 5. Risk register

Likelihood (L) and impact (I): 1 low – 3 high; score = L × I.

| ID | Risk | L | I | Score | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| RK-01 | Database rule change breaks a role’s access | 2 | 3 | 6 | 278 SQL checks; re-runnable files; backup before paste | Technical lead |
| RK-02 | Internet or Supabase outage during the games | 2 | 3 | 6 | Paper score sheets as fallback; enter results afterwards; status page monitoring | Salingkusog team |
| RK-03 | Wrong official result published | 2 | 3 | 6 | Medals need staff confirmation; corrections recompute the tally; audit of team | Managing Editor |
| RK-04 | Admin account compromised | 1 | 3 | 3 | Invite-only; deactivate quickly; MFA recommended (R-03) | Super admin |
| RK-05 | Free-tier limits exceeded during peak traffic | 2 | 2 | 4 | Edge cache; CDN; monitor usage [TO CONFIRM plan limits] | Technical lead |
| RK-06 | Knowledge loss when developers graduate | 3 | 2 | 6 | This documentation; developer guide; simple stack | Adviser |
| RK-07 | No CI lets a regression reach production | 2 | 2 | 4 | Gates in workflow; add CI (R-05) | Technical lead |
| RK-08 | Privacy complaint about published athlete data | 1 | 2 | 2 | Minimal data; consent for photos; update /privacy (R-10, R-12) | Executive Editor |
| RK-09 | Spam on public forms | 2 | 1 | 2 | Turnstile, rate limits, moderation | Editors |
| RK-10 | Vendor lock-in (Supabase/Vercel) | 1 | 2 | 2 | Plain PostgreSQL schema; standard React app | Technical lead |

# 6. Cost and resources

| Item | Plan | Cost |
| --- | --- | --- |
| Supabase | Database, Auth, Storage, Realtime | [TO CONFIRM plan and monthly cost] |
| Vercel | Hosting, functions | [TO CONFIRM plan] |
| Cloudflare Turnstile | CAPTCHA | Free tier |
| Domain | [TO CONFIRM] | [TO CONFIRM] |
| Software | Open-source libraries (MIT/Apache licences) | none |
| People | Developer(s), editorial reviewers, adviser | [TO CONFIRM] |
| Hardware | Personal laptops and phones | none |

# 7. Change log

Merged branches by date (from git log --merges):

| Date | Merged into develop |
| --- | --- |
| 2026-04-12/13 | feature/admin, feature/article-card, feature/article-details-page |
| 2026-10-17 | feature/db-v2-schema, feature/tooling-design-system, feature/auth-staff, feature/public-shell-home, feature/section-pages, feature/article-page, feature/search-archives, feature/submissions-contact, feature/cms-shell-dashboard, feature/cms-article-editor, feature/cms-editorial-workflow, feature/cms-media-library, feature/cms-people-board, feature/cms-site-settings, feature/seo-sharing, feature/v2-polish, feature/upgrade-tiptap-3, feature/upgrade-vite-7, feature/perf-pass, feature/salingkusog-db, feature/salingkusog-team-access, feature/salingkusog-cms-setup, fix/router-test-timeout, content/media-organization-copy, docs/phase2-plan, docs/release-pr |
| 2026-10-18 | feature/salingkusog-scorekeeper, -medal-tally, -schedule, -winners, -factions, -sports-bracket, -match-recap, -venues, -countdown, feature/sports-landing, feature/countdown-launch, feature/countdown-redesign, feature/nav-more-menu, feature/section-news, -feature, -literary, -blogs, -specials, -views, -science-technology, -investigative, -explainer, -bulletin, -stories, feature/statistics, feature/brand-tokens-fonts, -header-footer, -header-tagline, -components, -pages, -lime-hover, feature/literary-folio-photo, feature/logo-loader, perf/edge-cache-images, fix/nested-dialog-close, fix/server-esm-imports, fix/sk-more-categories, docs/pr-track-a, docs/stats-vercel-analytics, docs/track-b-wrapup |
| 2026-10-19 | feature/sk-chart-animations, feature/sk-points-race-ranges, feature/publish-permissions, fix/security-hardening, feature/sk-official-tally, feature/turnstile-captcha, feature/sk-auto-brackets, feature/sk-contests, fix/build-schedule-individual, fix/pre-release-polish, docs/pr-brand-2026, docs/pr-auto-brackets |

Releases to main: pull requests #1, #2, #4, #5 and #6 (merge commits on main); #6 released everything up to commit d7f6f34.

# 8. Lessons learned

- Putting rules in the database made late changes (Business Manager role, publishing access) safe: one helper, tests, done.

- Re-runnable SQL removed deployment fear but requires discipline about order when access is narrowed.

- Fixture screens (/dev) let design and accessibility be checked without real data.

- A short pre-release review found real gaps (game form, schedule dates) that tests had not.